## Slide 1: OTS TRAINING

## Slide 2: Project Scope
Purpose: The purpose of this instruction is to review the order and ensure accurate truck configuration design and build that meets the customer expectations.
Scope: This instruction applies to the Pre-Con process within REV Fire Group; all business units.
  OTS (order to ship)
    Reduce time from order acceptance to engineering design and release.
    Implement new upfront process steps:
      Sales and Engineering review
      Pre-Con participation by cross functional team

## Slide 3: Outputs
Engineering and Sales expertise in Pre-Con meeting drives customer confidence.
Cross functional participation offers real time information on feasibility and pricing.
Live updates to sales drawing during Pre-Con contributes to customer engagement and clarification.
A signed Change Order (CO A) at the conclusion of Pre-Con avoids delays and finalizes order.
Engineering reviews non-standard options, if necessary, suggests alternate options that most closely meets customer intent.
“Clean order” requirement (no open issues) before transition from sales to engineering .
Standard work, documents and processes to be utilized to ensure standardization.

## Slide 4: Process Map
Future State:
Note:
Timeline shown above will be impacted and vary by backlog.
Delivery penalty starts on the 11th day after Pre-Con Change Order and updated drawings submitted to the dealer.
Price penalty starts on the 46th day after Pre-Con Change Order and updated drawings submitted to the dealer.
Day 0
Day 5
Day 45
Day 55
Change Order signed
Price penalty added (1% of contract price)
Delivery penalty added
(1 day for each day late until Order Release)
Order Released
Order Acceptance
Pre-Con Scheduled
Pre-Con Conducted
Change Order and updated drawings provided
Day 45
Day 90

## Slide 5: Flow Chart

## Slide 6: Pre-Con Change Policy
In the event any of the changes listed below are requested, the Pre-Con meeting will need to be rescheduled.
The dealer will need to generate a new quote for the apparatus in the latest price slot/data book.
The new quote will then need to be resubmitted though the standard upfront review process prior to submitting as an order.
The new order will be subjected to the current delivery guideline.
A new Pre-Con meeting will need to be scheduled.

## Slide 7: Pre-Con Change Policy
Length & Height Restriction
Equipment Allowance
Hose load change impacting design
Product Type (Pumper, Tanker, Rescue, etc.)
Aerial Device model
Custom Cab or Commercial chassis model
Major drivetrain (4x4, tandem axle, frame rails, torque box, axles, suspension, exhaust, etc.)
Generators and Idle Reduction Systems
Major electrical system changes
Water tank capacity Body Material
Body Structure (Body style, compartment design, rear end design, staircase design, hosebed style, roof top storage design, etc.)
Ladder Storage (location, make-model, length, quantity)
Pump Module structure (Top/Side Mount, Enclosed pump panel, Crosslay/Speedlay, Storage module, etc.)
Pump brand and model
Major plumbing (CAFS, SAM, etc.)
Customer/dealer supplied items
Configuration and Design changes to be avoided at Pre-Con meeting:

## Slide 8: Spec Review
  Individual Reviews
    Inside Sales and functional engineering teams shall complete the Individual Reviews of the order and flag options with questions, suggestions and/or concerns.

## Slide 9: Pre-Con Package
Updated specs, drawings, weights, Pre-Con review questions/concerns/suggestions shall be sent to the dealer ten days prior to the Pre-Con meeting.
Paint chips will also be sent to dealer as soon as available for customer approval.
The Contract Admin will issue Pre-Con meeting agenda reflecting discussion items and policies.

## Slide 10: Pre-Con Meeting
    Pre-Con meeting to be held with representation from engineering support functions.
    Dealer leads the Pre-Con meeting utilizing the updated spec.
    Contract Admin to populate Change Order as items are identified and discussed during the meeting.

## Slide 11: Pre-Con Meeting Conclusion
    Priced change order and updated drawings will be provided.
    It is expected that dealer and customer representatives with authority to sign the change order by the conclusion of the Pre-Con meeting.
    If the change order needs to be taken from the meeting for final review and signature, it is expected to have it signed and returned within 10 calendar days.
    If the change order is not signed by then, an additional day per day will be added to the promised delivery date.
    Additionally, an increase of 1% of the contract price will be added to the order, if the change order is not signed within 45 calendar days of receiving it.
    Paint chips need to be signed and approved by customer.
    Lettering, striping, graphics, paint break details need to be provided by the customer.
    Any outstanding items should be clearly defined with responsibility, expectations and deadline for completion.

## Slide 12: Post Pre-Con
Updated drawings, specs, pricing will be sent to dealer for final confirmation prior to order release.
Outstanding items like signed graphics layout, etc. need to be finalized within the prescribed timeline.
Estimated truck completion (subject to change) will be provided to the dealer/customer.

## Slide 13: QUESTIONS?
THANK YOU